## Materials
Item | Vendor/supplying plant | Purchasing Document | Document Date | Material_Code | Material_Name | Nature | UOM | Available_Qty | Received Quantity | Balance To Be Received | Balance Qty - Expected Delivery Date
1 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8003100 | CUMIFURAN SYRUP LIQUID RESIN | Adhesive | KG | 5025 | 5025 | 0 | Order Complete
2 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8003099 | CUMIFURAN FN POWDER | Adhesive | KG | 10150 | 10150 | 0 | Order Complete
3 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005758 | CUMIBON 105 - 240X115X30MM | Brick | NO | 42420 |  | 42420 | 2026-05-25
4 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8003100 | CUMIFURAN SYRUP LIQUID RESIN | Adhesive | KG | 5875 | 5875 | 0 | Order Complete
5 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8003099 | CUMIFURAN FN POWDER | Adhesive | KG | 12075 | 12075 | 0 | Order Complete
6 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005759 | CUMIBON 105 - 240X115X63MM | Brick | NO | 41470 | 31104 | 10366 | 2026-05-25
7 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005760 | PHENACIN A SYRUP | Adhesive | KG | 10700 |  | 10700 | Production Clearance will be provided after getting Handover Confirmation due to limited shelf life
8 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005761 | PHENACIN ACP POWDER | Adhesive | KG | 21650 |  | 21650 | Production Clearance will be provided after getting Handover Confirmation due to limited shelf life
9 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005762 | AR BRICKS - 230X115X30MM | Brick | NO | 10080 |  | 10080 | 2026-05-20
10 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005760 | PHENACIN A SYRUP | Adhesive | KG | 17050 |  | 17050 | Production Clearance will be provided after getting Handover Confirmation due to limited shelf life
11 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005761 | PHENACIN ACP POWDER | Adhesive | KG | 34700 |  | 34700 | Production Clearance will be provided after getting Handover Confirmation due to limited shelf life
12 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005763 | AR BRICKS - 230X115X40MM | Brick | NO | 143000 | 133056 | 9944 | 2026-05-20
13 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005764 | CUMIFLOOR ECO PRIMER | Adhesive | KIT | 30 |  | 30 | 2026-05-30
14 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005765 | CUMICRETE PU MF 300 (3MM) | Adhesive | KIT | 565 |  | 565 | 2026-05-30
15 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005766 | CUMICRETE PU MF 300 (1MM) | Adhesive | KIT | 249 |  | 249 | 2026-05-30
16 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005764 | CUMIFLOOR ECO PRIMER | Adhesive | KIT | 91 |  | 91 | 2026-05-30
17 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005767 | CUMICRETE PU MF 300 (5MM) | Adhesive | KIT | 1997 |  | 1997 | 2026-05-30
18 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005766 | CUMICRETE PU MF 300 (1MM) | Adhesive | KIT | 761 |  | 761 | 2026-05-30
19 | 110341 CARBORUNDUM UNIVERSAL LIMITED | 4720002728 | 2026-01-08 | GI-8005762 | AR BRICKS - 230X115X30MM | Brick | NO | 85120 | 47880 | 37240 | 2026-05-20
20 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6002001 | CHEMOLINE 4 E CN - 4 x 1100 x 10000 mm ( | Rubber Sheet | M2 | 17716 | 2112 | 15604 | 10-June-2026 - 4200 Sqm, Balance quantity ETA to be received from RTT | We have Ex-Stock 1000 Sqm 4mm 4ECN Rubber Sheet & Adhesive, which was bought for other project and same can be utilized to startup the job
21 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6000012 | BC 3004 (9 KG) | Adhesive | EA | 809 |  | 809 | 15-June-2026 - 30% Quantity, Balance quantity ETA to be received from RTT
22 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6000005 | HARDENER E-40 30 GR | Adhesive | EA | 9706 |  | 9706 | 15-June-2026 - 30% Quantity, Balance quantity ETA to be received from RTT
23 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6000013 | PRIMER PR 304 - 10 KG | Adhesive | EA | 243 |  | 243 | 15-June-2026 - 30% Quantity, Balance quantity ETA to be received from RTT
24 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6002242 | CARBON FILLER - (25KG) | Adhesive | BAG | 717 | 99 | 618 | 2026-06-15
25 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6002243 | COROFLAKE EP PRIMER COMP A (14 KG) | Adhesive | DR | 678 | 96 | 582 | 2026-06-15
26 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6002244 | COROFLAKE EP PRIMER COMP B (7 KG) | Adhesive | DR | 678 | 94 | 584 | 2026-06-15
27 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6002245 | SOLVENT T200 - (8KG) | Adhesive | DR | 91 | 13 | 78 | 2026-06-15
28 | 110201 TIP TOP Oberflächenschutz Elbe GMBH | 4720002729 | 2026-01-08 | GI-6002241 | SOLVENT CF-CE-(8.4KG) | Adhesive | EA | 106 |  | 106 | 2026-06-15
|  |  |  | GI-6000027 | Solvent | Toluene | KG | 2000 |  | 2000